## حالة الملفات
Batch | Case | Edge Function | Audit | Compliance | Refactor | Approved | Version | Notes
Batch 01 | 2026-02-01 | submit-online-order | ✅ | 0.94 | 2 | ✓ | 1 | 2 مخالفة واردة في ملف الفحص
Batch 01 | 2026-02-02 | update-order | ✅ | 0.91 | 2 | ✓ | 1 | يوجد ملاحظات وتحسين
Batch 01 | 2026-02-03 | confirm-order | ✅ | 0.98 | 1 | ✓ | 1 | يوجد اقتراح | 1.1
Batch 01 | 2026-02-04 | create-runsheet | ✅ |  |  | ✓
Batch 01 | 2026-02-05 | force-unassign-runsheet | ✅ |  |  | ✓
Batch 01 |  | Batch Status | ✅ |  |  | ✅ |  | Closed
Batch 02 |  | README | ✅ |  |  | ✅
Batch 02 | Case 02-01 | start-picking | ✅ |  |  | ✅ |  | Closed
Batch 02 | Case 02-02 | complete-picking | ✅ |  |  | ✅ |  | Closed
Batch 02 | Case 02-03 | cancel-picking | ✅ |  |  | ✅ |  | Closed
Batch 02 | Case 02-04 | reopen-picking | ✅ |  |  | ✅ |  | Closed
Batch 02 |  | Batch 02 | ✅ |  |  | ✅ |  | Closed
Batch 03 |  | start-loading | ✅ |  |  | ✅ |  | Closed
Batch 03 |  | complete-loading | ✅ |  |  | ✅ |  | Closed
Batch 03 |  | cancel-loading | ✅ |  |  | ✅ |  | Closed
Batch 03 |  | reopen-loading | ✅ |  |  | ✅ |  | Closed
Batch 04 |  | create-runsheet | ✅ |  |  | ✅ |  | Closed
Batch 04 |  | force-unassign-runsheet | ✅ |  |  | ✅ |  | Closed
Batch 04 |  | sync-run-sheet-details | ✅ |  |  | ✅ |  | Closed
Batch 04 |  | unload-runsheet | ✅ |  |  | ✅ |  | Closed
Batch 05
Batch 06
Batch 06 |  | ✅ start-return | ✅ |  |  | ✅
Batch 06 |  | ✅ complete-return | ✅ |  |  | ✅
Batch 06 |  | ✅ cancel-return | ✅ |  |  | ✅
Batch 06 |  | ✅ reopen-return | ✅ |  |  | ✅
Batch 06 |  | ✅ create-credit-note | ✅ |  |  | ✅
Batch 07 |  | save-daily-settlement | ✅ | 98 |  | ✅
Batch 07 |  | report-discrepancy | ✅ | 99 |  | ✅
| Function | Score
Note on J4: MOHAMED HASSAN: في حالة تعديلها مرة ثانية

## Batch Register-لوحة القيادة
Batch | Workflow | Cases | Contains | النتيجة | Status | Compliance | Closed | ملاحظات | ملف الفحص
Batch 01 | Order Lifecycle (بداية دورة الحياة) | 5 | * submit-online-order * update-order * confirm-order * create-runsheet * force-unassign-runsheet | • اعتماد دورة حياة Order. • اعتماد نقطة بداية الأحداث. | Approved | 96% | Closed | مع تسجيل أربع ملاحظات معمارية للتحسين، دون وجود أي مانع للاستمرار. | Batch 01 — Order Lifecycle\تقرير الفحص
Batch 02 | Picking Workflow | 4 | * start-picking * complete-picking *cancel-picking * reopen-picking | • اعتماد حدث Picking Completed. • مراجعة الحجز فقط دون خصم المخزون. | Approved | 95% | Closed | لا توجد أخطاء معمارية كبيرة. لكن لدي اقتراحين لتحسين الجودة. | Batch 02 — Picking Workflow\تقرير الفحص
Batch 03 | Loading Workflow | 5 | start-loading complete-loading cancel-loading reopen-loading sync-run-sheet-details | النتيجة: • اعتماد حدث Loading Completed. • اعتماد العلاقة بين: o Orders o RunSheet o Stock o Accounting وهذا سيكون أكبر مراجعة معمارية. | Approved | 98% | Closed | لا توجد مخالفات معمارية تمنع اعتماد Batch. | تقرير الفحص Batch 03
Batch 04 | Runsheet Engine | 4 | create-runsheet (تم الانتهاء منها) في Batch 01 وتقييمها approved sync-run-sheet-details (تم الانتهاء منها) وتقييمها approved force-unassign-runsheet (تم الانتهاء منها) في Batch 01 وتقييمها approved unload-runsheet | اعتماد: • Runsheet Lifecycle • Projection Layer • Driver Assignment • Route Structure • Runsheet Source Of Truth | Approved |  |  |  | تقرير الفحص Batch04
Batch 05 | Delivery Engine | 6 | start-delivery complete-delivery start-order-delivery complete-order-delivery cancel-delivery cancel-order-delivery save-delivery-item | اعتماد Delivery Completed ↓ Invoice ↓ Revenue ↓ COGS ↓ Customer Ledger | Approved | 95% | Closed |  | تقرير الفحص Batch 05
Batch 06 | Returns Engine | 5 | start-return complete-return cancel-return reopen-return create-credit-note | المرتجعات | Approved | 95% | Closed |  | تقرير الفحص Batch 06
Batch 07 | Settlement Engine | 2 | save-daily-settlement report-discrepancy |  | Approved | 98% | Closed |  | تقرير الفحص Batch 07
Batch 08 | Inventory Engine | 9 | create-stock-voucher send-stock-voucher receive-stock-voucher complete-stock-voucher cancel-stock-voucher receive-purchase save-purchase-order bulk-stock-adjustment save-inventory-count | الأذونات المخزنية | Deferred – Phase 2 Batch08 = Pending P0 الأولوية P0 / P1 / P2 (كما صنفتها في التقرير) |  | مؤجل | سبب التأجيل: "يُنفذ بعد اكتمال مراجعة جميع الـ Batches لضمان تصميم حل موحد." بهذا نحقق هدفين: ننتهي أولًا من فحص المشروع بالكامل واكتشاف جميع المشاكل. ننفذ الإصلاحات مرة واحدة بشكل متناسق، بدلًا من ترقيعات متفرقة.يوجد تعديلات | تقرير الفحص Batch 08
Batch 09 | Batch 09 — Accounting Engine | 3 | save-journal-entry |  |  |  | Conditionally Approved |  | تقرير الفحص Batch 09
10 | Batch10 Master Data |  | save-item delete-item save-customer delete-customer save-supplier delete-supplier save-employee delete-employee save-branch delete-branch save-category save-role delete-role save-settings |  | Approved |  | Closed |  | تقرير الفحص Batch 10
11 | System Configuration Engine |  | save-settings تم نقلها الي Batch 10 seed-roles تم نقلها الي Batch 13 seed-stock-branches تم نقلها الي Batch 13 setup-van-branch تم نقلها الي Batch 13 | تم الالغاء لنقل الدوال لملفات اخري
12 | Reporting Engine |  | get-profit-loss get-balance-sheet get-cash-flow get-trial-balance get-pnl-by-cost-center get-driver-dashboard |  | Approved | 98% | Closed | بعد إصلاح بسيط في get-driver-dashboard، يمكن اعتباره معتمداً بالكامل | تقرير الفحص Batch 12
13 | Batch13 Infrastructure | 1 | log-action seed-roles seed-stock-branches setup-van-branch |  | Approved |  | Closed |  | تقرير الفحص Batch 13
14 | Batch14 Treasury | 3 | save-payment-voucher save-receipt-voucher save-transfer-voucher |  | Approved |  | Closed |  | تقرير الفحص Batch 14
15 | دوال منسية |  | append-to-runsheet cancel-receiving cancel-unload delete-order reopen-receiving save-sales-invoice start-receiving update-driver-ledger

## Sheet1
1 | confirm-order- Batch 01 - Order Lifecycle (بداية دورة الحياة)
2 | create-runsheet- Batch 01 - Order Lifecycle (بداية دورة الحياة) - Batch 04 - Runsheet Engine
3 | force-unassign-runsheet- Batch 01 - Order Lifecycle (بداية دورة الحياة) - Batch 04 - Runsheet Engine
4 | submit-online-order- Batch 01 - Order Lifecycle (بداية دورة الحياة)
5 | update-order- Batch 01 - Order Lifecycle (بداية دورة الحياة)
6 | cancel-picking- Batch 02 - Picking Workflow
7 | complete-picking- Batch 02 - Picking Workflow
8 | reopen-picking- Batch 02 - Picking Workflow
9 | start-picking- Batch 02 - Picking Workflow
10 | cancel-loading- Batch 03 - Loading Workflow
11 | complete-loading- Batch 03 - Loading Workflow
12 | reopen-loading- Batch 03 - Loading Workflow
13 | start-loading- Batch 03 - Loading Workflow
14 | sync-run-sheet-details- Batch 03 - Loading Workflow - Batch 04 - Runsheet Engine
15 | unload-runsheet- Batch 04 - Runsheet Engine
16 | cancel-delivery- Batch 05 - Delivery Engine
17 | cancel-order-delivery- Batch 05 - Delivery Engine
18 | complete-delivery- Batch 05 - Delivery Engine
19 | complete-order-delivery- Batch 05 - Delivery Engine
20 | save-delivery-item- Batch 05 - Delivery Engine
21 | start-delivery- Batch 05 - Delivery Engine
22 | start-order-delivery- Batch 05 - Delivery Engine
23 | cancel-return- Batch 06 - Returns Engine
24 | complete-return- Batch 06 - Returns Engine
25 | create-credit-note- Batch 06 - Returns Engine
26 | reopen-return- Batch 06 - Returns Engine
27 | start-return- Batch 06 - Returns Engine
28 | report-discrepancy- Batch 07 - Settlement Engine
29 | save-daily-settlement- Batch 07 - Settlement Engine
30 | bulk-stock-adjustment- Batch 08 - Inventory Engine
31 | cancel-stock-voucher- Batch 08 - Inventory Engine
32 | complete-stock-voucher- Batch 08 - Inventory Engine
33 | create-stock-voucher- Batch 08 - Inventory Engine
34 | receive-purchase- Batch 08 - Inventory Engine
35 | receive-stock-voucher- Batch 08 - Inventory Engine
36 | save-inventory-count- Batch 08 - Inventory Engine
37 | save-purchase-order- Batch 08 - Inventory Engine
38 | send-stock-voucher- Batch 08 - Inventory Engine
39 | save-journal-entry- Batch 09 - Batch 09 — Accounting Engine
40 | delete-branch- Batch 10 - Batch10 Master Data
41 | delete-customer- Batch 10 - Batch10 Master Data
42 | delete-employee- Batch 10 - Batch10 Master Data
43 | delete-item- Batch 10 - Batch10 Master Data
44 | delete-role- Batch 10 - Batch10 Master Data
45 | delete-supplier- Batch 10 - Batch10 Master Data
46 | save-branch- Batch 10 - Batch10 Master Data
47 | save-category- Batch 10 - Batch10 Master Data
48 | save-customer- Batch 10 - Batch10 Master Data
49 | save-employee- Batch 10 - Batch10 Master Data
50 | save-item- Batch 10 - Batch10 Master Data
51 | save-role- Batch 10 - Batch10 Master Data
52 | save-settings- Batch 10 - Batch10 Master Data
53 | save-supplier- Batch 10 - Batch10 Master Data
54 | get-balance-sheet- Batch 12 - Reporting Engine
55 | get-cash-flow- Batch 12 - Reporting Engine
56 | get-driver-dashboard- Batch 12 - Reporting Engine
57 | get-pnl-by-cost-center- Batch 12 - Reporting Engine
58 | get-profit-loss- Batch 12 - Reporting Engine
59 | get-trial-balance- Batch 12 - Reporting Engine
60 | log-action- Batch13 - Infrastructure
61 | seed-roles- Batch13 - Infrastructure
62 | seed-stock-branches- Batch13 - Infrastructure
63 | setup-van-branch- Batch13 - Infrastructure
64 | save-payment-voucher- Batch14 - Treasury
65 | save-receipt-voucher- Batch14 - Treasury
66 | save-transfer-voucher- Batch14 - Treasury
67 | append-to-runsheet- Batch15 - دوال منسية
68 | cancel-receiving- Batch15 - دوال منسية
69 | cancel-unload- Batch15 - دوال منسية
70 | delete-order- Batch15 - دوال منسية
71 | reopen-receiving- Batch15 - دوال منسية
72 | save-sales-invoice- Batch15 - دوال منسية
73 | start-receiving- Batch15 - دوال منسية
74 | update-driver-ledger- Batch15 - دوال منسية

## Architecture Findings Register
السجل الرسمي للديون المعمارية (Architectural Technical Debt Register). المخالفات المكتشفة
ID | Severity | Function | Issue | Decision | Status
A-001 | Medium |  |  | Static Company UUID | Open
A-002 | Medium |  |  | Sequence Generation داخل الدوال | Open
A-003 | Low |  |  | Missing Event Engine | Open
A-004 | Low |  |  | Delete & Reinsert في update-order | Open
Split complete-return
Transaction Wrapper
|  |  |  | COA Configuration | Deferred | P6
|  |  |  | Ledger Refactor | Deferred | P6
[5 empty] | Deferred | P7
[5 empty] | Deferred | P8

## Constitution Compliance
Rule | Description | Checked | Violations
AC-01 | Single Source of Truth | ✓ | 0
AC-02 | Event Driven | ✓ | 1
AC-03 | No Static UUID | ✓ | 3
AC-04 | Inventory Rules | ✓ | 0
AC-05 | Accounting Matrix | ✓ | 0